## Slide 1: Step 7 and 8. Monitoring and re-adjusting
Antónia de Barros Mota (Toyah)
Eva Turró Font
Martina Teschnarová
Health & Hygiene Promotion in Emergencies

## Slide 2
Objectives of the session
Formulate objectives related to health and hygiene promotion activities​
List out key points to consider when formulating health and hygiene behaviour objectives​
Understanding the tools used when formulating health and hygiene behaviour objectives
Notes: CHECK

## Slide 4
- WASH guidelines for hygiene promotion in emergency operations. IFRC, 2017
STEP 7 MONITORING
Monitoring is important to demonstrate progress
All the team should be involved and must understand the monitoring process
Should be part of the training programme for volunteers
Involve the affected population in the monitoring
Indicators are used to track progress
Monitor not only if results are being achieved but also if the objectives are aligned with the needs
message

## Slide 5
Monitoring and Evaluation Planning. American Red Cross, USAID, 2008
When monitoring starts?

## Slide 6
Spanish Red Cross Training on Hygiene promotion in emergencies, 2022 - WASH guidelines for hygiene promotion in emergency operations. IFRC, 2017
Difference between monitoring and evaluation
It examines what the project/programme has achieved, whether it has met the objectives and what changes have occurred as a result of the intervention.
Routine collection and analysis of information to monitor the progress of established plans and objectives.
Monitoring
Evaluation

## Slide 7
Spanish Red Cross Training on Hygiene promotion in emergencies, 2022 Evaluation of higiene promotion. Mooijman. 2003
MONITORING PLAN What to consider
Human and financial resources
Monitoring calendar
Strategy for reporting results
Tools
for data collection
Collect and record data, decisions
Qualitative and Quantitative data
PGI, CEA, Cash transfer, Other sectors...
Notes: The monitoring plan should include timelines, a budget, staff and responsibilities, and indicators. Indicators should be developed as soon as possible.
Tools for collecting information should be qualitative and quantitative.
Monitor community participation including vulnerable groups. Involve community and stakeholders in monitoring where possible.
Data should be disaggregated by gender, age and disability.
Only use as much information as necessary, avoid over-collecting or over-bothering.
1. Human and financial resources needed to carry out routine monitoring:
Frequency of programme activities: How often will monitoring activities be carried out?
will be carried out?
Available or attainable human resources: How many staff members are needed to carry out monitoring in line with the needs identified by the frequency of programme activities? Monitoring can be carried out by senior programme staff as well as by implementers in the field.
Financial resources: What funds are available to carry out the necessary monitoring tasks?
2. Develop a monitoring calendar:
Use the programme activities as a basis for developing the monitoring calendar.
Choose a time unit for monitoring (e.g. weekly, bi-weekly, monthly, bi-monthly, quarterly) that is appropriate for the duration of the programme and within the limits of available resources.
Set specific objectives for each point in programme planning/implementation at which monitoring will take place.
3. Develop a data collection tool
Since the data for monitoring will mostly come from programme records, simple checklists or reporting forms can be used to collect the necessary information. These forms should be easy to fill in and transfer to official programme reports.
4. Developing a practical strategy for reporting monitoring results
Once the data has been collected, the next step is to report the results.
Each programme must decide to whom the monitoring results should be provided and how they should be distributed. Normally, the report is internal and is intended for the country team; however, regional and other senior staff, or funding agency staff, may be included.
Ideally, the monitoring data collection sheet should be easily transferable to a report. The structure of the two documents should therefore be closely related.
Typically, summary statistics, which are basic descriptors of the data. Examples of basic descriptors are simple counts (e.g. 12 hygiene promoters recruited), or percentages/proportions (e.g. 98% of households were visited by a hygiene promoter).

## Slide 8
WASH guidelines for hygiene promotion in emergency operations. IFRC, 2017
MONITORING PLAN Indicators
In planning we were developing the indicators that were related to the objectives of the intervention.
Now for the monitoring plan we need to establish the means of verification and the frequency.

## Slide 9
Spanish Red Cross Training on Hygiene promotion in emergencies, 2022 - Compendium on Hygiene Promotion in Emergencies, WASH network, WASH cluster, IFRC, SSA, 2022
TOOLS Types of data collection
Voting chart
Community mapping
Interviews
Surveys, questionnaires
Observation
FGD
Transect walks

## Slide 10
www.watsanmissionassistant.org
TOOLS Monitoring formulary

## Slide 11
www.watsanmissionassistant.org
TOOLS Indicator tracking table

## Slide 12
www.watsanmissionassistant.org
TOOLS Feedback system

## Slide 13
TOOLS Post Distribution Monitoring Survey

## Slide 14
  Let’s see how we are doing!
  MONITORING PLAN

## Slide 15
EXERCISE 1 – 30 min
Complete the table with the indicators for Malawi
Notes: Activity: complete the table

## Slide 17
WASH guidelines for hygiene promotion in emergency operations. IFRC, 2017
STEP 8 REVIEW AND RE-ADJUST
Go back to your initial assumption and strategy to re-steer your intervention to make it more effective and efficient
Continuous assessment, re-planning and re-adjustment of activities are essential
Make sure the activities are still relevant to the needs
Baseline, midline, endline
message

## Slide 18
Spanish Red Cross Training on Hygiene promotion in emergencies, 2022
Documentation and handover
Record all work and share with all actors involved (ERU, SN, IFRC, Donors)
GRC format
IFRC format
Lessons learned
Documentation methods
Reports
Pictures
Short videos

## Slide 19
  life is change!
  RE-ADJUST

## Slide 20
You were conducting a feedback mechanism with the community that is working really well.
Three month after your intervention you do a revision of the feedback received from community members from two affected areas within the last two weeks (through different feedback mechanisms).
After you have reviewed and discussed the feedback, elaborate on key adjustments you should undertake to ensure your objectives are reached.
EXERCISE 2 – 30 min
Notes: Activity2 :

## Slide 21
 | The ORP is not providing me with the medicines I need for my leg |  | When I go to the ORP I don’t know how to keep my child safe, it’s not a place for children!
 | The ORP is not functioning at night time |  | I went to the ORP because I have skin rash and fever, they didn’t help me!
 | The ORP is inside the school and I can’t access |  | The volunteers are not from my community, they don’t speak my language, that is very disrespectful!
 | At the school there are some girls that are not attending because of harassment |  | I am in love with you lovely volunteer, you stole my heart and now I can’t sleep! Find me near the river at 19h!
 | The director of the school is asking favours to the community coming to the ORP in exchange for oral rehydration solution |  | I have rash all over my body and runny nose, maybe not diarrhea, but I want ORS like the others!
 | The ORP is my favourite thing in the community, can we make it nicer and we paint it red? Red is my cat’s name! |  | I recommend that the ORP has also treatment for the skin, all my family is having rash and we need treatment!
 | The other day I dreamt about getting cholera in the ORP, I think they are not safe anymore, I will tell the religious leader about it |  | The ORP is smelly as hell!
Community A
Community B
Notes: Tips community A:
- access
- violence
- rumour follow-up
-PGI
Tips community B:
- new disease in the community
- involvement with beneficiaries
- training the right volunteers
- hygiene at the ORP
- treatment criteria at the ORP

## Slide 22
RESOURCES - TOOLS
https://watsanmissionassistant.org/emergency-hygiene/
Notes: https://watsanmissionassistant.org/emergency-hygiene/

## Slide 23
 Muchas Gracias
Muito Obrigada
Moc děkuji 